## Sheet1
System Name: | RxPress Pharmacy System
Members: | Ahito, Bernadeth Claire G.
Coca, Juvie R.
Del Mar, Kiana Marquisa S.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  |  | September | [10 empty] | October | [31 empty] | November
Tasks | Assignee | Date Started | Date Finished | Status | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | ... | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 27 | 28 | 29 | 30
1. User Registration and Authentication | Kiana Marquisa S. Del Mar
1.1. Design UI | Kiana Marquisa Del Mar | 2024-09-15 | 2024-09-30 | Done
1.2. Integrate with DB | Kiana Marquisa Del Mar | 2024-09-30 | 2024-10-29 | Done
1.3 Implement Security Measures | Kiana Marquisa Del Mar | 2024-09-30 | 2024-10-29 | Done
1.4 Testing | Kiana Marquisa Del Mar | 2024-10-27 | 2024-10-29 | Done
2. Profile Management | Bernadeth Claire G. Ahito
2.1 Design UI/UX Figma | Bernadeth Claire Ahito | 2024-09-04 | 2024-09-11 | Done
2.3 Integrate with Database | Bernadeth Claire Ahito | 2024-09-29 | 2024-10-09 | Done
2.4 Develop Password Management Features | Bernadeth Claire Ahito | 2024-10-07 | 2024-10-11 | Done
2.5 Implement Data Validation | Bernadeth Claire Ahito | 2024-10-11 | 2024-10-15 | Done
2.10 Account Deactivation and Deletion | Bernadeth Claire Ahito | 2024-10-16 | 2024-10-20 | Done
2.11 Testing | Bernadeth Claire Ahito | 2024-11-06 | 2024-11-10 | Done
3. Order Management | Juvie R. Coca
3.1 Design UI | Juvie Coca | 2024-09-04 | 2024-09-04 | Done
3.3 Integrate with Database | Juvie Coca | 2024-10-05 | 2024-11-01 | In progress
3.5 Create an Order View | Juvie Coca | 2024-10-30 | 2024-11-01 | In progress
4. Shopping Cart & Checkout Process | Bernadeth Claire G. Ahito
4.1 Design UI | Bernadeth Claire Ahito | 2024-09-04 | 2024-09-20 | Done
4.1.1 Wireframes for the shopping cart and checkout page | Bernadeth Claire Ahito | 2024-10-07 | 2024-10-21 | Done
4.1.2 Components | Bernadeth Claire Ahito | 2024-10-08 | 2024-10-19 | Done
4.2 Implement Request Submission Logic | Bernadeth Claire Ahito | 2024-10-12 | 2024-10-25 | Done
4.2.1 Add to Cart | Bernadeth Claire Ahito | 2024-10-15 | 2024-10-26 | Done
4.2.2 Update Cart: | Bernadeth Claire Ahito | 2024-10-15 | 2024-10-26 | Done
4.2.3 Remove from Cart | Bernadeth Claire Ahito | 2024-10-18 | 2024-10-29 | Done
4.2.4 Checkout Process: | Bernadeth Claire Ahito | 2024-10-30 | 2024-11-03 | Done
4.3 Integrate with Database | Bernadeth Claire Ahito | 2024-10-29 | 2024-11-03 | Done
4.3.1 Database Migration | Bernadeth Claire Ahito | 2024-11-06 | 2024-11-10 | Done
4.3.2 Testing Integration | Bernadeth Claire Ahito | 2024-11-15 | 2024-11-20 | In progress
5. Medicine Catalog | Juvie R. Coca
5.1 Design UI | Juvie Coca | 2024-09-04 | 2024-09-04 | Done
5.3 Integrate with Database | Juvie Coca | 2024-10-05 | 2024-11-01 | Done
5.4 Implement a filterable list of medicine | Juvie Coca | 2024-11-01 | 2024-11-05 | In progress
6. Admin | Kiana Marquisa S. Del Mar
6.1 Design UI | Kiana Marquisa Del Mar | 2024-10-30 | 2024-11-16 | Done
6.2 Develop Medicine Inventory Logic | Kiana Marquisa Del Mar | 2024-10-30 | 2024-11-16 | Done
6.3 Integrate with Database | Kiana Marquisa Del Mar | 2024-10-30 | 2024-11-17 | Done
6.3.1 Database Migration | Kiana Marquisa Del Mar | 2024-10-31 | 2024-11-17 | Done
6.3.2 Testing Migration | Kiana Marquisa Del Mar | 2024-10-31 | 2024-11-17 | Done
6.4 Implement Medicine Inventory Logic | Kiana Marquisa Del Mar | 2024-11-03 | 2024-11-17 | Done
6.4.1 Display Medicine | Kiana Marquisa Del Mar | 2024-11-03 | 2024-11-17 | Done
6.4.2 Add Medicine | Kiana Marquisa Del Mar | 2024-11-03 | 2024-11-17 | Done
6.4.3 Edit Medicine | Kiana Marquisa Del Mar | 2024-11-03 | 2024-11-17 | Done
6.4.4 Delete Medicine | Kiana Marquisa Del Mar | 2024-11-03 | 2024-11-17 | Done
6.5 Testing | Kiana Marquisa Del Mar | 2024-11-18 |  | In progress